## 25 Projects
BU/Division | Planned | Urgency/Priority | Project Name | Project Manager | Est. Start Date | Actual Start Date | Est. Delivery Date | Revised Delivery Date | Actual Delivery Date | Completion % | Completed
Chemicals | Yes | 1 | Fleet Planning (Phase 1) Finance | Nassim Samad | 2024-01-01 |  | 2025-05-01 |  |  | 100% | Completed
Digital | Yes | 1 | Fleet Planning (Phase 2) Chemicals / Dry Bulk | Nassim Samad | 2025-07-01 |  | 2025-12-01 |  |  | 10% | Canceled
Chemicals | Yes | 2 | Seaber Scheduling & Optimization | Aravind | 2025-05-07 | 2025-05-07 | 2025-10-30 | closed |  | 95% | In Progress
Chemicals | Yes | 3 | Immersive Experience (Digital Twin) | Tan Mudzaffar | 2024-01-01 |  | 2025-06-30 |  |  | 100% | Completed
Chemicals | Yes | 4 | Fuel EU Penalty Calculation | Sijin John | 2025-05-01 |  | 2025-09-30 |  |  | 100% | Completed
Chemicals | Yes | 5 | EU ETS Module in Trading and Risk for Carbon Emission | Sijin John | 2024-11-15 |  | 2025-04-25 |  |  | 100% | Completed
Chemicals | Yes | 6 | Laytime and Demurrage Automation | Sijin John | 2025-06-01 |  | 2025-10-30 |  |  | 100% | Completed
Chemicals | Yes | 7 | Break-Even Analysis | Santhi Venkateswaran | 2025-06-01 | 2025-10-20 | 2025-12-31 |  |  | 100% | Completed
Digital | Yes |  | APIGEE Migration | Mohammed Alawad | 2025-01-01 |  | 2026-03-26 |  |  | 90% | In Progress
Digital | Yes |  | Digital: Consolidate All Dashboard in one hub / Fabric Migration | Santhi Venkateswaran | 2025-07-01 | 2025-08-01 | 2025-12-31 |  | 2025-08-31 | 100% | Completed
Digital | No |  | DTMO - Digital Projects Tracker Sheet & Dashboard | Fatima Alqahtani | 2025-05-20 |  | 2025-07-15 |  |  | 100% | Completed
Digital | Yes | 1 | AutoML - Dataiku | Muhammad Arsalan | 2025-07-01 |  | 2025-12-31 |  |  | 100% | Completed
Digital | Yes |  | EA & DG Program | Julian Paglione | 2025-09-01 | 2025-09-01 | 2026-08-31 |  |  | 40% | In Progress
Digital | Yes | 1 | Master Data Management - Atacama | Julian Paglione |  | 2025-04-01 |  | 2025-12-31 |  | 0% | Not Started
Digital | Yes | 1 | Microsoft Fabric | Muhammad Arsalan | 2025-01-15 | 2025-01-15 | 2025-07-17 |  |  | 100% | Completed
Digital | No |  | Jira - Demand Managemnt Process | Fatima Alqahtani | 2025-04-16 |  | 2025-09-30 |  |  | 100% | Completed
Dry Bulk | Yes | 1 | Operations Performance Using Cockpit Phase 1 | Santhi Venkateswaran | 2025-03-01 |  | 2025-05-21 |  | 2025-06-04 | 100% | Completed
Dry Bulk | Yes | 1 | Operations Performance Using Cockpit Phase 2 | Muhammad Arsalan | 2025-08-15 |  | 2025-12-01 |  |  | 0% | Not Started
Dry Bulk | Yes | 2 | ML Based Advanced Freight Forecasting | Ikmal Azman | 2024-12-16 | 2024-12-16 | 2025-02-27 |  | 2025-02-27 | 100% | Completed
Dry Bulk | Yes | 2 | Enhance Work Productivity through AI (Copilot) | Ikmal Azman | 2025-03-11 | 2025-03-11 | 2025-04-07 |  | 2025-04-07 | 100% | Completed
Dry Bulk | Yes | 3 | Consolidate All Dashboard in one hub / Fabric Migration | Santhi Venkateswaran | 2025-07-01 | 2025-08-01 | 2025-09-30 |  | 2025-08-05 | 100% | Completed
Dry Bulk | Yes | 1 | Invoicing Process Optimization Phase 1 | Tan Mudzaffar | 2025-07-27 |  | 2025-12-31 |  |  | 100% | Completed
Dry Bulk | Yes | 2 | AI-Driven Market Data Scanning (Copilot) | Ikmal Azman | 2025-06-16 |  | 2025-09-30 |  |  | 100% | Completed
Dry Bulk | Yes |  | Marcura: Claimhub | Muhammad Arsalan | [5 empty] | 0% | Canceled
Dry Bulk | Yes | 1 | Auto Filing of Shipping Documents via RPA | Tan Mudzaffar | 2024-08-01 |  | 2025-01-10 |  |  | 100% | Completed
Finance | No | 1 | Uniqus project ( Stream 1 - Data Governance and Management Framework) | Tan Mudzaffar | 2025-03-01 |  | 2025-08-14 |  |  | 100% | Completed
Finance | No | 1 | Uniqus project (Stream 2: Implementation of Executive Dashboards + KPI Framework ) | Santhi Venkateswaran | 2025-04-17 | 2025-04-17 | 2025-08-14 |  | 2025-08-10 | 100% | Completed
Finance | No | 1 | Uniqus project (Internal Dashboard Development - Post Stream 2) | Santhi Venkateswaran | 2025-08-11 | 2025-10-01 | 2025-12-31 | 2025-02-28 |  | 98% | In Progress
Finance | No | 1 | Uniqus project (stream 3: Bank Reconcilation) | Khalid Albakr | 2025-05-01 |  | 2025-07-27 |  |  | 100% | Completed
Finance | No | 2 | Implement Financial Modules ERP system (Singapore Office) | Upendra Tirakala | 2025-03-01 |  | 2025-03-30 |  |  | 100% | Completed
Finance | Yes | 2 | EPM project - Phase 1 | Ahmed Abdalslam | 2025-02-18 |  | 2025-08-30 | 2025-03-30 |  | 95% | In Progress
Finance | Yes | 2 | Treasury Roadmap (FIS System) | Munwar Saeed | 2025-03-03 |  | 2025-06-30 |  | 2025-08-07 | 100% | Completed
Finance | Yes | 2 | Automation of SADAD Payments | Walid Fathi | 2025-01-01 |  | 2025-03-30 |  |  | 100% | Completed
Finance | Yes | 2 | Cash Projection Dashboard - Tresury (Phase 1 ) | Santhi Venkateswaran | 2025-01-01 | 2025-01-01 | 2025-01-31 |  | 2025-01-31 | 100% | Completed
Finance | Yes | 2 | Cash Projection Dashboard - Tresury ( Phase 2) | Santhi Venkateswaran | 2025-05-09 | 2025-05-09 | 2025-12-31 |  |  | 100% | Completed
Finance | Yes | 2 | Investor Relationship | Njoud Alfarraj | 2025-04-04 |  | 2025-11-30 |  |  | 100% | Completed
Finance | No |  | Implement new Business Unit under BL Legal Entity (Agency BU) | Upendra Tirakala | 2025-04-02 |  | 2025-06-30 |  |  | 70% | Canceled
Finance | No |  | Implement Indian Tax | Upendra Tirakala | 2025-02-01 |  | 2025-03-30 |  |  | 100% | Completed
Finance | No |  | Insurance New System | Walid Fathi | [5 empty] | 0% | Canceled
Finance | No |  | Exeption Report | Santhi Venkateswaran | 2025-02-01 | 2025-02-01 | 2025-09-30 |  | 2025-09-30 | 100% | Completed
Finance | Yes |  | Implement Virtual IBAN | Upendra Tirakala | 2025-06-30 |  | 2025-09-30 |  |  | 100% | Completed
Finance | Yes |  | Implement Budget Control 2026 | Mohammed Desouky | 2025-11-02 | 2025-12-15 | 2025-12-15 |  |  | 100% | Completed
Finance | Yes |  | Automating VAT return filling | Walid Fathi | [5 empty] | 0% | Canceled
Finance | No |  | Implement new Legal Entity BAHRI LOGISTICS (SILZ) LLC - GL Module | Mohammed Desouky | 2025-11-02 |  | 2025-11-13 |  |  | 100% | Completed
Finance | No |  | Implement new Legal Entity Bahri High Seas - GL, AP and Tax modules | Mohammed Desouky | 2025-11-16 |  | 2025-12-18 |  |  | 100% | Completed
Legal & Board Secretary | Yes |  | Contract Legal Review and Archiving Solutions | Noura Alrakban | 2025-07-01 |  | 2025-11-01 |  |  | 100% | Completed
Legal & Board Secretary | Yes |  | Board of Dirctors payments | Noura Alrakban | 2025-07-01 |  | 2025-10-01 |  |  | 100% | Completed
Logistics | Yes | 1 | CRM for Line and Air | Sara Shahin | 2025-02-01 |  | 2025-10-15 |  |  | 100% | Completed
Logistics | Yes | 1 | Agency Software implementation (GAT_SHIP) | Ali Alrezgan | 2025-02-01 |  | 2025-10-01 |  |  | 100% | Completed
Logistics | Yes | 1 | New Line System | Fatima Alqahtani | [5 empty] | 10% | Canceled
Logistics | Yes | 1 | CSY Project | Ibrahim Alboiez | 2025-01-01 |  | 2025-09-30 |  |  | 100% | Completed
Logistics | Yes | 1 | Air Cargo Management System | Ali Alrezgan | [5 empty] | 0% | Canceled
Logistics | No | 1 | Logistics Financial Integration Hub | Ali Alrezgan | 2025-07-01 |  | 2026-02-28 |  |  | 90% | In Progress
Logistics | Yes | 2 | Bahri Line website | Noura Alrakban | 2025-09-01 |  | 2025-11-30 |  |  | 5% | Canceled
Logistics | No |  | Implement Agency Business Unit under BL | Walid Fathi | 2025-01-01 |  | 2025-06-30 |  |  | 100% | Completed
Logistics | Yes |  | Bahri Integrated Logistics Business Group (Seperation) | Khalid Albakr | [5 empty] | 0% | Canceled
Logistics | No |  | Logistics OHI | Nuha Aldossari | 2025-01-01 |  | 2025-06-30 |  |  | 100% | Completed
Oil | Yes | 3 | Automate TI report | Santhi Venkateswaran | 2025-02-10 | 2025-02-10 | 2025-02-24 |  | 2025-02-24 | 100% | Completed
Oil | Yes | 2 | Automating line up reports for ports. | Santhi Venkateswaran | 2025-03-03 | 2025-03-03 | 2025-03-27 |  | 2025-03-27 | 100% | Completed
Oil | Yes | 2 | Automate LOI tracking sheet | Santhi Venkateswaran | 2025-05-01 | 2025-06-17 | 2025-08-28 |  | 2025-08-28 | 100% | Completed
Oil | Yes | 2 | Automate Monthly KPI sheet | Santhi Venkateswaran | 2025-04-15 | 2025-05-08 | 2025-06-03 |  | 2025-06-03 | 100% | Completed
Oil | Yes | 1 | Budget vs Actual Model - Phase 2 Enhancements | Santhi Venkateswaran | 2025-03-03 | 2025-03-03 | 2025-07-29 |  | 2025-07-29 | 100% | Completed
Oil | Yes | 1 | Market Intelligence Model - Phase 2 Enhancements | Santhi Venkateswaran | 2025-04-21 | 2025-05-01 | 2025-06-25 |  | 2025-06-25 | 100% | Completed
Shared Services | No | 1 | Integration between Fusion and Paylocity (United States Office) |  | 2025-07-01 |  |  |  |  | 0% | Not Started
Shared Services | Yes | 1 | SCM: Implementation of Monthly Auto Accrual for UAE Ledger | Walid Fathi | 2025-01-01 | 2025-01-01 | 2025-01-31 |  | 2025-01-31 | 100% | Completed
Shared Services | Yes | 1 | SCM: Supplier Qualification & Performance Management | Walid Fathi | 2025-02-16 | 2025-02-16 | 2025-06-30 |  | 2025-06-30 | 100% | Completed
Shared Services | Yes | 1 | SCM: Sourcing Module Implementation for RFQ Automation | Walid Fathi | 2025-06-01 | 2025-06-23 | 2025-06-30 |  | 2025-07-31 | 100% | Completed
Shared Services | No | 1 | SCM: Implementation of Oracle Self-service Procurement Module for Logistics DWC-LLC. | Walid Fathi | 2025-07-01 | 2025-10-07 | 2025-11-30 |  | 2025-11-30 | 100% | Completed
Shared Services | No | 1 | SCM: Implementation of Oracle Purchasing Module for Logistics DWC-LLC. | Walid Fathi | 2025-08-01 | 2025-10-07 | 2025-11-30 |  | 2025-11-30 | 100% | Completed
Shared Services | No | 2 | SCM: Implementation of Oracle Self-service Procurement Module for Singapore. | Kashif Ahmed | 2025-12-01 |  | 2026-01-31 |  |  | 100% | Completed
Shared Services | No | 2 | SCM: Implementation of Oracle Purchasing Module for Singapore. | Kashif Ahmed | 2025-12-01 |  | 2026-01-31 |  |  | 100% | Completed
Shared Services | Yes | 1 | MyBahri & Bahar AI (Web Portal & Mobile App) | Sumiyah Fallatah | 2025-01-01 |  | 2026-01-29 |  |  | 100% | Completed
Shared Services | Yes | 1 | My Bahri Portal Phase 3 | Sumiyah Fallatah | 2025-11-01 |  | 2026-12-15 |  |  | 100% | Completed
Shared Services | Yes | 2 | Bahri External Portal Revamp - Phase 1 | Noura Alrakban | 2025-09-01 |  | 2026-05-31 |  |  | 100% | Completed
Shared Services | Yes | 2 | Event Management Sytstem | Noura Alrakban | 2025-09-01 |  | 2025-12-31 |  |  | 100% | Completed
Shared Services | Yes |  | IAM | Mohammed Alawad | 2025-01-01 |  | 2025-06-30 |  |  | 80% | Canceled
Shared Services | No |  | HR OHI Group1 (Greeting Card, Sugessions & complains) | Sumiyah Fallatah | 2025-01-01 |  | 2025-03-30 |  |  | 100% | Completed
Shared Services | No |  | Strategy: Business Performance dashboard | Santhi Venkateswaran | 2025-01-01 | 2025-01-01 | 2025-12-31 |  | 2025-10-10 | 100% | Completed
Shared Services | No | 1 | HCM: Implement new Legal Entity (Singapore Office) | Ahmed Habib | 2025-03-01 | 2025-03-01 | 2025-03-31 |  | 2025-03-31 | 100% | Completed
Shared Services | No | 3 | HCM: Enhance HCM Modules (United States Office) | Ahmed Habib | 2025-05-01 | 2025-05-01 | 2025-11-30 |  |  | 10% | Canceled
Shared Services | No | 1 | HCM: General and Administrative Expenses (G&A) | Ahmed Habib | 2025-04-01 | 2025-04-01 | 2025-06-30 |  | 2025-07-01 | 100% | Completed
Shared Services | Yes | 1 | HCM: Bahri Logistics DWC Payroll | Ahmed Habib | 2025-01-01 | 2025-01-01 | 2025-01-31 |  | 2025-01-31 | 100% | Completed
Shared Services | Yes | 1 | HCM:Performance and Compensation | Ahmed Habib | 2025-01-01 | 2025-01-01 | 2025-05-31 |  | 2025-05-31 | 100% | Completed
Shared Services | Yes | 1 | HCM: Recruitment Process Automation System | Ahmed Habib | 2025-01-01 | 2025-01-01 | 2025-03-30 |  | 2025-05-31 | 100% | Completed
Shared Services | Yes | 2 | HCM: Integration with UAE Banks [Monthly Payroll Payment ] | Ahmed Habib | 2025-08-01 | 2025-08-01 | 2025-10-20 |  | 2025-10-20 | 100% | Completed
Shared Services | No | 2 | HCM: Integration with UAE Banks [weekly Payroll Payment ] | Ahmed Habib | 2025-11-01 | 2025-11-01 | 2025-12-31 |  |  | 30% | In Progress
Shared Services | Yes | 1 | HCM: LinkedIn Integration with Oracle Recruiting Cloud | Ahmed Habib | 2025-03-01 | 2025-03-01 | 2025-07-31 |  | 2025-10-31 | 100% | Completed
Shared Services | No | 2 | HCM: Business Training Need Analysis [BTNA] | Ahmed Habib | 2025-09-01 | 2025-09-01 | 2025-12-15 |  |  | 100% | Completed
Shared Services | No | 2 | HCM: LinkedIn Integration with Oracle Talent Profile | Ahmed Habib | 2025-03-01 | 2025-03-01 | 2025-12-31 |  |  | 100% | Completed
Shared Services | No | 3 | HCM: HCM Dashboard | Ahmed Habib | 2025-02-01 | 2025-02-01 | 2025-12-31 |  |  | 100% | Completed
Shared Services | No | 1 | HCM: Securing HCM Reports implementation | Ahmed Habib | 2025-02-01 | 2025-02-01 | 2025-05-31 |  | 2025-05-31 | 100% | Completed
Shared Services | No | 1 | HCM: ORACLE Time and Labor [OTL] - Setup Change | Ahmed Habib | 2025-10-15 | 2025-11-12 | 2026-01-31 |  |  | 100% | Completed
Shared Services | No | 2 | HCM: India Payroll for UAE Ledger | Ahmed Habib | 2025-10-01 | 2025-11-05 | 2026-01-31 |  |  | 100% | Completed
Shared Services | No | 1 | Finance: Implement new Legal Entity BAHRI LOGISTICS (SILZ) LLC and BAHRI HIGH SEAS. | Ahmed Habib | 2025-11-05 | 2025-11-08 | 2025-11-10 |  | 2025-11-10 | 100% | Completed
Shared Services | No | 1 | HCM: Implement ORACLE Fusion Core HR & Absence Management for Singapore Office | Ahmed Habib | 2025-10-15 | 2025-10-15 | 2025-11-01 |  | 2025-11-01 | 100% | Completed
Shared Services | No | 2 | HCM: System Enhancements – (Total of 107) | Ahmed Habib | 2025-01-01 |  | 2025-12-31 |  |  | 100% | Completed
Shared Services | No | 2 | HCM: Reports & Dashboard & HCM Extract | Ahmed Habib | 2025-01-01 |  | 2025-12-31 |  |  | 100% | Completed
Shared Services | Yes |  | Recruiting Solution | Ali Alrezgan | [5 empty] | 0% | Canceled
Shared Services | Yes |  | Salt Communication App | [6 empty] | 0% | Canceled
Ship Management | Yes | 1 | SMS on intranet (AI powered search) Phase 1 | Muhammad Arsalan | 2025-02-17 |  | 2025-11-21 | 28th Feb |  | 98% | In Progress
Ship Management | Yes | 3 | Smart SMS Gap analysis & revision request Phase 1 | Muhammad Arsalan | 2025-02-17 |  | 2025-11-21 | 28th Feb |  | 98% | In Progress
Ship Management | Yes | 4 | Automate weekly, monthly and quarterly reports | Santhi Venkateswaran | [5 empty] | 0% | Canceled
Ship Management | Yes | 2 | Vendor Invoice Variance Analysis | Santhi Venkateswaran | 2025-02-17 | 2025-08-11 | 2025-09-30 |  | 2025-09-25 | 100% | Completed
Ship Management | Yes | 2 | High Frequency Data (2024) | Muhammad Arsalan | 2025-06-30 |  | 2025-09-10 |  |  | 100% | Completed
Ship Management | Yes | 1 | Vessels Scoring | Santhi Venkateswaran | 2025-03-15 | 2025-03-15 | 2025-12-31 |  | 2025-07-05 | 100% | Completed
Ship Management | Yes | 3 | Smart Troubleshooting Phase 1 | Muhammad Arsalan | 2025-02-17 |  | 2025-11-21 | 28th Feb |  | 98% | In Progress
Ship Management | Yes | 1 | Engine Performance | Muhammad Arsalan | 2025-06-02 |  | 2025-12-31 |  |  | 100% | Completed
Sustainability & GRC | Yes | 1 | Enterprise risk management (ERM) software | Noura Alrakban | 2025-05-16 |  | 2025-12-30 |  |  | 100% | Completed
Sustainability & GRC | Yes | 2 | Environmental, Social, and Governance (ESG) software | Noura Alrakban | 2025-05-16 |  | 2025-12-30 |  |  | 100% | Completed
Digital | Yes |  | EA Tool implementation | Julian Paglione | 2025-09-01 | 2025-09-01 | 2025-12-31 |  |  | 100% | Completed
Chemicals | Yes | 4 | The Veslink forms to capture the daily reporting from Vessels is also being tested as a part of this project. | Sijin John | 2025-10-16 |  | 2025-12-15 |  |  | 100% | Completed
Sustainability & GRC | Yes | 3 | Complince Software (KYC) | Fatima Alqahtani | 2025-09-26 |  |  |  |  | 100% | Completed
Logistics | No | 1 | WMS/SEB EDIFACT Integration | Mohammed Alawad | 2025-09-25 |  | 2026-03-12 |  |  | 100% | Completed